## Sheet1
Lofthus frukt og saft
Project Leader
Holmfridur Hjaltadottir | Project start | 2019-11-11
| Project end | 02.13.19
[6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14
Task |  | Progress | Start | End | Days | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16
1 Meeting. |  |  |  |  | 1
Planning for 2 Meeting. |  |  |  |  | 11
Get staff. |  |  |  |  | 5
Staff meeting. |  |  |  |  | 1
Get Server service. |  |  |  |  | 1
Create a Wireframe. |  |  |  |  | 8
Fonts, Colors. |  |  |  |  | 3
2 Meeting. |  |  |  |  | 1
Staff meeting. |  |  |  |  | 1
Get info about Lofthus. |  |  |  |  | 1
Staff meeting. |  |  |  |  | 1
Design website/code. |  |  |  |  | 57
Take Photos. |  |  |  |  | 14
Make video. |  |  |  |  | 22
Write text for site. |  |  |  |  | 20
3 Meeting. |  |  |  |  | 1
Find flaw´s and fix. |  |  |  |  | 14
Last Meeting. |  |  |  |  | 1
Launch website. |  |  |  |  | 0
Holmfridur Hjaltadottir
front-End developer
Graphic designer
Photographer/film maker
Writer
Everyone